## Instructions
Workflow Estimation Tool Instructions
This document should be completed as part of the technical design specification for workflow development. The technical
design specification for a workflow will not be considered complete until the workflow estimation tool is completed.
The workflow developer will document the estimated objects required in the workflow estimation tool and store the document
with the workflow group leader and in the project document repository (Compass or MDM). Upon completion of the
workflow code review the workflow developer will update the workflow estimation tool with the actuals from the development
activities and store this updated document with the workflow group leader and in the project document repository (Compass
or MDM).
Specific Instructions for Completing the Workflow Estimation Tool
The workflow development estimation worksheet is protected to prevent inadvertant deleting of formulas and fields. The
workflow developer is required to enter this information as part of the workflow technical specification documentation
activities. Enter a number in the 'Estimated Number of Objects' column that represents the initial estimated number of
objects required for the activity.
Some fields are self calculating and therefore will not require input from the workflow developer. These fields are indicated
as such.
Upon completion of the estimation please save it with a file name that includes the project and send a copy of the estimation
to the workflow group leader. The document must also be stored with the workflow technical design specification as part of
the project deliverables.
Upon completion of the workflow technical specification (completion of workflow development and testing), the workflow
developer will update the estimation document with the actual numbers of objects developed and the actual number of
person days used for the effort. This updated document will be sent to the workflow group leader and stored as part of the
project documentation deliverables.
The workflow estimation tool is a living document that will undergo many changes as we gather data and refine it. Please
feel free to include any comments relating to adding or removing objects as you work with this estimation tool. Comments
should be directed to the workflow group leaders.

## Constants
WF Estimation Tool Constants
Constant Name | Value
Project name | zmyProject
Resorce productivity level (%) | 70%
(H)igh level of difficulty weight (%) | 100%
(M)edium level of difficutly weight (%) | 75%
(L)ow level of difficulty weight (%) | 50%
Additional resource impact for technical spec/design | 1
Additional resource impact for development | 0.75
Additional resource impact for technical code review/documentation | 0.75
Additional resource impact for unit/integration testing | 1

## ABAP Dev. Est. Worksheet
ABAP Estimation for zmyProject | Estimated Number of Objects | Difficulty Lvl (H)igh (M)edium (L)ow | Estimated Person Days | Estimation Effort * | Actual Number of Objects | Actual Person Days | % Completed | Comments / Notes
Technical Design Specifications
Enter number of technical design specifications (1/main ABAP Program) | 1 | M | 7.5 | 10 days/spec
Technical design specification review |  |  | 0.75 | 1 days/spec
Execution of action items from technical design review - Adjustments to ABAP design! |  |  | 1.5 | 2 days/spec
ABAP Object Coding and Definition (assuming 1 ABAP Object per main application)
ABAP Object Key Field identification and definition
Enter the estimated number of ABAP Object key fields | 0 | H | 0 | 0.4 days/key field
ABAP Object Attribute coding and definition
Enter the estimated number of ABAP Object database attributes | 0 | H | 0 | 0.4 days/db attribute
Enter the estimated number of ABAP Object virtual attributes | 0 | H | 0 | 2 days/virtual attribute
ABAP Object Method coding
Enter the estimated number of ABAP Object methods to be developed from scratch | 0 | H | 0 | 2 days/method
ABAP Object Event identification and definition
Enter the estimated number of custom event triggers to be defined (for raising WF events) | 10 | M | 15 | 2 days/event trigger |  |  |  | Capturing Oject Event raising and Stauts management (I.e. FM, MCS Appr req.)
ABAP Object Master Data Create / Update
Enter the estimated Master Data Add / Update | 0 | H | 0 | 2 days/create / update
GUI Program Identification and Definition
Enter the estimated number of GUI Programs | 0 | M | 0 | 4 days/Main Program
Enter the estimated number of T-CODES | 0 | M | 0 | 0.7 days/t-code
Enter the estimated number of Screens / Forms | 0 | M | 0 | 1 days/screen / form
Enter estimated number of Athurization - Security | 8 | M | 6 | 1 days/security auths
Tables
Enter the estimated number of custom tables | 0 | M | 0 | 7.5 days/tables
Enter the estimated number of custom relationships | 0 | M | 0 | 1 days/main program
Table structure technical design review |  |  | 0 | 1 days/table struct review
Execute of action items from table struct review |  |  | 0 | 2 days/review
Enter the number of CRUD (Create, Read, Write, Deletes, Archive) | 0 | M | 0 | 0.5 days/definition
Misc. ABAP
Enter the estimated number of custom user exit integration | 0 | L | 0 | 1 days/per exit int.
Enter the estimated number of custom user functions | 0 | L | 0 | 20 days/function
Enter the estimated number of custom reports | 0 | L | 0 | 20 days/report
Technical Documentation
Estimated number of technical documents (1 document per main/major Program) | 1 | M | 3 | 4 days/doc
Workflow and workflow coding review |  |  | 1.5 | 2 days/review
Execution of action items from workflow and workflow coding review |  |  | 1.5 | 2 days/review
Unit Testing (derived from cell B34)
ABAP unit test | 1 | H | 5 | 5 days/program
Execution of action items as a result of unit testing |  |  | 2 | 2 days/program
Integration Testing
Enter the number of t-codes that require integration testing | 1 | H | 6.6 | 6.6 days/t-code
Execution of action items as a result of integration testing |  |  | 2 | 2 days/t-code
WF Development coordination
Put an 'X' in this box if the Program is required to interact with WF | X | L | 1.1625 | Add 10% more effort
Web Development
Put an 'X' in this box if the Program is required to run on the web |  | H | 0 | Add 40% more effort
* Effort days/%s listed represent (H) difficulty (100%) and will reflect fewer person days if a (M) or (L) difficulty level is assessed
(projected technical spec/design days) |  |  | 9.75
(projected development days) |  |  | 22.1625
(projected technical code review/documentation days) |  |  | 6
(projected unit/integration testing days) |  |  | 15.6
Total Estimated Person/Days (effort) |  |  | 53.5125
70% Productivity Factor Adjustment |  |  | 16.0538
Total Adjusted Estimated Person/Days (Estimated + Adjustment) |  |  | 69.5662
Estimated Person/Months (duration) |  |  | 3.4783

## WF Dev. Est. Worksheet
Workflow Estimation for zmyProject | Estimated Number of Objects | Difficulty Lvl (H)igh (M)edium (L)ow | Estimated Person Days | Estimation Effort * | Actual Number of Objects | Actual Person Days | % Completed | Comments / Notes
Technical Design Specifications
Enter number of technical design specifications (1/main workflow template) | 1 | M | 7.5 | 10 days/spec |  |  | 0.5 | Roughly 50% of the design has been completed. Do to the design spread over many months we will need to revisit all issues to finalize technical design specs.
Technical design specification review |  |  | 0.75 | 1 days/spec
Execution of action items from technical design review - Adjustments to WF design! |  |  | 1.5 | 2 days/spec
BOR Coding and Definition (assuming 1 business object per main workflow)
BOR Interface coding
Enter the estimated number of BOR interfaces (IFFIND, IFSTATUS, etc.) | 1 | L | 0.15 | 0.3 days/interface
BOR Key Field identification and definition
Enter the estimated number of BOR key fields | 1 | L | 0.2 | 0.4 days/key field
BOR Attribute coding and definition
Enter the estimated number of BOR database attributes | 6 | M | 1.8 | 0.4 days/db attribute
Enter the estimated number of BOR virtual attributes | 0 | M | 0 | 2 days/virtual attribute
BOR Method coding
Enter the estimated number of BOR methods using existing R/3 functionality | 0 | M | 0 | .75 days/method
Enter the estimated number of BOR methods using modified R/3 functionality | 0 | M | 0 | 1.75 days/method
Enter the estimated number of BOR methods to be developed from scratch | 4 | L | 8 | 4 days/method
BOR Event identification and definition
Enter the estimated number of BOR events | 7 | L | 0.875 | 0.25 days/event
Enter the estimated number of existing event triggers to be defined | 0 | M | 0 | 0.5 days/event trigger
Enter the estimated number of custom event triggers to be defined | 6 | L | 6 | 2 days/event trigger
Enter the estimated number of event filters | 0 | M | 0 | 0.6 days/event filter
Enter the estimated number of event receivers | 1 | L | 0.3 | 0.6 days/event receiver
Single Step Task Identification and Definition
Enter the estimated number of single step tasks | 6 | M | 4.95 | 1.1 days/single step task
Agent Assignment
Enter the number of occurrences of the following agent assignment techniques for each task and workflow that require agent assignment.
Exclusively using an existing organizational structure | 0 | M | 0 | 0.7 days/assignment
Use of an existing R/3 role | 0 | M | 0 | 1 days/role
Development of a custom role resolution solution | 0 | M | 0 | 3 days/role
Use of an existing R/3 function module | 4 | M | 3.6 | 1.2 days/function module
Use of a custom developed function module | 1 | L | 1.65 | 3.3 days/function module |  |  |  | EDI, DPC and DLA
Workflow Template Definition
Enter the estimated number of workflow templates | 1 | M | 5.625 | 7.5 days/wf template
Organizational Structure Definition
Org structure technical design document (1 document per main/major workflow taken from cell B3) | 1 | M | 0.75 | 1 days/main workflow
Org structure technical design review |  |  | 0.75 | 1 days/org structure
Execute of action items from org structure review |  |  | 1.5 | 2 days/review
Enter the number of organizations, jobs, and/or positions to define | 0 | M | 0 | 0.2 days/definition
Technical Documentation
Estimated number of technical documents (1 document per main/major workflow taken from cell B3) | 1 | M | 3 | 4 days/doc
Workflow and workflow coding review |  |  | 1.5 | 2 days/review
Execution of action items from workflow and workflow coding review |  |  | 1.5 | 2 days/review
Unit Testing (derived from cell B34)
Workfow unit test (derived from cell B34) | 1 | M | 3.75 | 5 days/workflow
Execution of action items as a result of unit testing |  |  | 1.5 | 2 days/workflow
Integration Testing
Enter the number of workflows that require integration testing | 1 | M | 4.95 | 6.6 days/workflow
Execution of action items as a result of integration testing |  |  | 1.5 | 2 days/workflow
Web Development
Put an 'X' in this box if the workflow is required to run on the web | 0 | H | 0 | Add 40% more effort
* Effort days/%s listed represent (H) difficulty (100%) and will reflect fewer person days if a (M) or (L) difficulty level is assessed
(projected technical spec/design days) |  |  | 9.75
(projected development days) |  |  | 36.15
(projected technical code review/documentation days) |  |  | 6
(projected unit/integration testing days) |  |  | 11.7
Total Estimated Person/Days (effort) |  |  | 63.6
70% Productivity Factor Adjustment |  |  | 19.08
Total Adjusted Estimated Person/Days (Estimated + Adjustment) |  |  | 82.68
Estimated Person/Months (duration) |  |  | 4.134

## Totals
Estimate Totals for zmyProject
ABAP Estimation for zmyProject | Est. ABAP Level of Effort (Person Days/Hours) |  | Est. ABAP Time to Completion (Person Days/Months)
| Est.Person Days | Raw Est. Person Hours (8 hr day) | 30% Prod. Factor Adj.Person Days | Total Adjusted Est Person Days | Total Est Person Mos.
Projected technical spec/design days/hours | 9.75 | 78 | 2.925 | 12.675 | 0.63375
Projected development days/hours | 22.1625 | 177.3 | 6.6487 | 28.8113 | 1.4406
Projected technical code review/documentation days/hours | 6 | 48 | 1.8 | 7.8 | 0.39
Projected unit/integration testing days/hours | 15.6 | 124.8 | 4.68 | 20.28 | 1.014
ABAP Total: | 53.5125 | 428.1 | 16.0538 | 69.5662 | 3.4783
Workflow Estimation for zmyProject | Est. Workflow Level of Effort (Person Days/Hours) |  | Est. Workflow Time to Completion (Person Days/Months)
| Est.Person Days | Raw Est. Person Hours (8 hr day) | 30% Prod. Factor Adj.Person Days | Total Adjusted Est Person Days | Total Est Person Mos.
Projected technical spec/design days/hours | 9.75 | 78 | 2.925 | 12.675 | 0.63375
Projected development days/hours | 36.15 | 289.2 | 10.845 | 46.995 | 2.3497
Projected technical code review/documentation days/hours | 6 | 48 | 1.8 | 7.8 | 0.39
Projected unit/integration testing days/hours | 11.7 | 93.6 | 3.51 | 15.21 | 0.7605
Workflow Total: | 63.6 | 508.8 | 19.08 | 82.68 | 4.134
Combined ABAP + Workflow Estimation for zmyProject | Est. Total Level of Effort (Person Days/Hours) |  | Est. Total Time to Completion (Person Days/Months)
| Est.Person Days | Raw Est. Person Hours (8 hr day) | 30% Prod. Factor Adj.Person Days | Total Adjusted Est Person Days | Total Est Person Mos.
Projected technical spec/design days/hours | 19.5 | 156 | 5.85 | 25.35 | 1.2675
Projected development days/hours | 58.3125 | 466.5 | 17.4937 | 75.8063 | 3.7903
Projected technical code review/documentation days/hours | 12 | 96 | 3.6 | 15.6 | 0.78
Projected unit/integration testing days/hours | 27.3 | 218.4 | 8.19 | 35.49 | 1.7745
Combined Total: | 117.1125 | 936.9 | 35.1337 | 152.2463 | 7.6123
Resourcing and Effect of assigning 'multiple' resources ('Actual' months to complete for 1 ABAP, 2 WF, 1 SD resource) |  |  | Type Resources assigned | # Resources assigned | Adj. Est. Months to completion
> 1 Technical spec/design resources assigned calculated as 1 additional resource |  |  | ABAP, WF, SD | 4 | 0.31688
> 1 Development resources calculated as 0.75 additional resource |  |  | ABAP, WF | 3 | 1.5161
> 1 Technical code review/documentation resources calculated as 0.75 additional resource |  |  | ABAP, WF | 3 | 0.312
> 1 Unit/integration testing resources calculated as 1 additional resource |  |  | ABAP, WF, SD | 4 | 0.44362
Combined Total: |  |  | 1 ABAP, 2 WF, 1 SD |  | 2.5886

## Revisions & Notes
Revision | Date | Person | Comments
1 | 2001-01-15 | D. Harmon | Initial release
1.1 | 2001-01-26 | D. Harmon | Added org structure documentation efforts, execution of action items for unit and integration testing
1.2 | 2001-08-10 | D. Harmon | Corrected problem with unit testing action item calculation
1.3 | 2002-06-19 | D. Harmon | Corrected problem with BOR interface calculation and event receiver calculation
1.4 | 2003-01-15 | D. Harmon | Corrected minor problems with calculations
1.5 | 2004-08-19 | D. Harmon | Decreased estimated times for action item execution after reviews, changed productivity factor adjustment to 70% and corrected total adjustment estimation calculation
1.6 | 2005-05-10 | R. Sample | Added column for % completed and Notes
This is a work in progress. We will be adding and adjusting to fit our needs.
If you require chnages, please let me know…
1.6 | 2005-05-11 | R.Sample | Column "B" is the ONLY column for data entry!!!
1.6 | 2005-05-11 | R.Sample | Column Color Coding
Column A:
Dark Gray - Group
Light Gray - Sub Group
Yellow - Lines that need data entry in Column B
1.7 | 2005-05-24 |  | Added ABAP Estimate form
1.8 | 2005-06-06 |  | Added 'Constants' worksheet
- Project nameused for sheet titles, etc
- Difficulty Lvl % weight values (H)igh (M)edium (L)ow
Added Difficulty Lvl (H)igh (M)edium (L)ow column to ABAP and WF dev sheets
Modified Estimated Person Days calculations to reflect assessed difficulty levels (H,M,L)
Noted that: *(Estimation) Effort days/%s listed represent (H) difficulty (100%) and will reflect fewer person days if a (M) or (L) difficulty level is assessed
1.9 | 2005-06-14 |  | 'Color coded' items that are estimated and added a 'subtotal' section on both ABAP Dev. Est. Worksheet and WF Dev. Est. Worksheet, calssified as follows:
(projected technical spec/design days)
(projected development days)
(projected technical code review/documentation days)
(projected unit/integration testing days)
Added 'Total's' worksheet